STEERING COMMITTEE · CUSTOMER PORTAL REPLATFORM

Customer Portal Replatform

Project plan · version 1.2

THE ANSWER Move 18,000 customer accounts to the new portal by 31 March 2027 for £1.35M, retiring the legacy stack and cutting support tickets by 30%.

| SPONSOR | Grace Mensah, Chief Customer Officer |
| --- | --- |
| PROJECT MANAGER | Luis Ortega, PMO |
| BUDGET | £1.35M capex · £180k contingency |
| TIMELINE | 1 November 2026 – 31 March 2027 |
| STATUS | Approved for mobilisation |

IN THIS DOCUMENT

| 01 | Objectives |
| --- | --- |
| 02 | Scope |
| 03 | Milestones |
| 04 | Roles and responsibilities |
| 05 | Risks |
| 06 | Governance |

# 1. Objectives

| Objective | Measure | Target | Baseline |
| --- | --- | --- | --- |
| Reduce support demand | Tickets per 1,000 accounts / month | ≤ 42 | 60 |
| Faster self-service | Median time to download an invoice | < 30 s | 2 min 40 s |
| Retire legacy stack | Legacy servers decommissioned | 100% | 0% |

# 2. Scope

| IN SCOPE • Account, billing and usage pages • SSO with customer identity providers • Migration of 18,000 accounts • Accessibility to WCAG 2.2 AA | OUT OF SCOPE • Mobile apps (FY28 roadmap) • Partner portal • Changes to the billing engine • New pricing plans |
| --- | --- |

# 3. Milestones

| # | Milestone | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| M1 | Discovery and architecture sign-off | L. Ortega | 22 Nov 2026 | Complete |
| M2 | Design system and prototypes tested | H. Kim | 13 Dec 2026 | On track |
| M3 | Beta with 500 accounts | S. Patel | 31 Jan 2027 | On track |
| M4 | Migration waves 1–3 | S. Patel | 10 Mar 2027 | At risk |
| M5 | Legacy decommissioned | R. Chen | 31 Mar 2027 | On track |

# 4. Roles and responsibilities

| Activity | Sponsor | PM | Engineering | Support |
| --- | --- | --- | --- | --- |
| Scope changes | A | R | C | I |
| Release go / no-go | A | R | C | C |
| Customer communications | I | A | I | R |
| Data migration | I | A | R | C |

R = responsible · A = accountable · C = consulted · I = informed

# 5. Risks

| Risk | Rating | Response | Owner |
| --- | --- | --- | --- |
| Data quality in legacy accounts delays migration | High | Cleansing sprint in December; automated validation | S. Patel |
| Enterprise SSO configurations vary widely | Medium | Early access for top 40 accounts | R. Chen |

# 6. Governance

Steering committee meets fortnightly; the PM issues a one-page status report every Friday. Changes above £25k or two weeks of schedule go to the sponsor for approval.