## Slide 1
PRODUCT STRATEGY
FY27 Product Roadmap
Three themes, sequenced Now / Next / Later
NOW
NEXT
LATER
Hannah Kim, VP Product · October 2026

## Slide 2
STRATEGY
Three themes carry FY27
Northwind Analytics · Product roadmap FY27
2
Self-serve analytics
Business users answer 80% of questions without an analyst.
• Natural-language query
• Metric catalogue
• Embedded dashboards
Goal: Activation +25%
Trusted data
Lineage, quality alerts and audit, so the numbers are believed.
• Quality alerts
• Column-level lineage
• Data contracts
Goal: Data incidents −50%
Enterprise ready
SSO, roles, residency and the SLAs the top 100 accounts need.
• SCIM provisioning
• EU + APAC residency
• 99.99% SLA tier
Goal: Enterprise win rate 35%

## Slide 3
ROADMAP
Roadmap: Now, Next, Later
Northwind Analytics · Product roadmap FY27
3
NOW · Q1
NEXT · Q2–Q3
LATER · Q4+
Self-serve analytics
Natural-language query beta
Metric catalogue GA
Embedded dashboards
Trusted data
Quality alerts
Column-level lineage
Data contracts
Enterprise ready
SCIM provisioning
EU + APAC residency
99.99% SLA tier
Filled = committed · outlined = planned, subject to discovery

## Slide 4
TIMELINE
Key milestones
Northwind Analytics · Product roadmap FY27
4
JAN
NL query beta
120 design partners
MAR
Quality alerts GA
All plans
MAY
SCIM + residency
Enterprise tier
AUG
Lineage GA
Column level
NOV
Embedded dashboards
Partner launch

## Slide 5
RISKS
Dependencies and risks
Northwind Analytics · Product roadmap FY27
5
Dependency / risk | Impacts | Rating | Mitigation | Owner
LLM provider cost per query | NL query | Medium | Caching + small-model routing | Platform
EU residency needs new region | Enterprise | High | Region build starts Q1 | Infra
Lineage parser coverage for dbt | Trusted data | Low | Partner with dbt Labs | Data
Design hiring (1 open lead role) | All themes | Medium | Contract agency for Q1 | Product