## Slide 1
BOARD OF DIRECTORS · 22 OCTOBER 2026
Q3 FY26 Board Update
Three decisions, one risk to note, and the quarter against plan
Daniel Okafor, CEO · Priya Raman, CFO Board confidential

## Slide 2
ASKS OF THE BOARD
This meeting asks the Board for three decisions
Northwind Analytics · Board update · Q3 FY26
2
APPROVE
FY27 operating plan
£48.6M revenue, 14.2% EBITDA margin
Owner: CFO · today
APPROVE
APAC hub — tranche 1
£2.1M capex, released January 2027
Owner: COO · today
NOTE
Enterprise churn above threshold
2 logos lost, £0.6M ARR; recovery plan on slide 5
Owner: CRO · Q4
DISCUSS
Pricing for FY27 renewals
Options A/B in the appendix
Owner: CEO · December

## Slide 3
QUARTER AT A GLANCE
Revenue is 6% ahead of plan; EBITDA is on plan
NOTE
Northwind Analytics · Board update · Q3 FY26
3
Q3 REVENUE
£11.2M
+6.1% vs plan · +19% YoY
EBITDA MARGIN
13.4%
+0.2 pts vs plan
NET REVENUE RETENTION
112%
−2 pts vs Q2
Chart: 
| Q4 FY25 | Q1 FY26 | Q2 FY26 | Q3 FY26
Plan (£M) | 9 | 9.6 | 10.1 | 10.55
Actual (£M) | 9.4 | 9.8 | 10.6 | 11.2

## Slide 4
WORKSTREAM STATUS
Two of five workstreams need Board attention
NOTE
Northwind Analytics · Board update · Q3 FY26
4
Core growth
ON TRACK
Pipeline cover 3.1× for H1; win rate 27%.
APAC launch
AT RISK
3 LOIs signed; GM hire slipping to January.
Enterprise retention
OFF TRACK
2 logos lost (£0.6M ARR); recovery plan live.
Platform reliability
ON TRACK
99.97% uptime vs 99.95% target.
Cost programme
ON TRACK
£1.1M of £1.4M savings banked.
Status thresholds
On track — within 5% of plan
At risk — 5–10% off plan or a date slips < 1 month
Off track — > 10% off plan or slips ≥ 1 month

## Slide 5
RISK REGISTER — EXCEPTIONS ONLY
Enterprise churn breached its threshold this quarter
NOTE
Northwind Analytics · Board update · Q3 FY26
5
Risk | Rating | Change | Mitigation | Owner
Enterprise churn above 8% threshold | High | ↑ new | Exec sponsor on top 25 accounts | CRO
Singapore GM hire slips past Q1 | Medium | ↑ | Interim GM seconded from London | COO
SGD cost exposure | Medium | → | Hedge 70% of committed spend | CFO
Key-person dependency in data platform | Low | ↓ | Two senior hires closed in Q3 | CTO
Green risks with no change since Q2 are in the appendix. Ratings use the Board-approved 5×5 likelihood × impact matrix.

## Slide 6
NEXT STEPS
Next steps: every action has an owner and a date
Northwind Analytics · Board update · Q3 FY26
6
Action | Owner | Due
Release APAC tranche 1 on Board approval | COO | Jan 2027
Report tranche-1 revenue gate progress | CFO | Apr 2027 Board
Present enterprise churn recovery results | CRO | Dec 2026 Board
Bring FY27 renewal pricing recommendation | CEO | Dec 2026 Board